## Example
Year-End Fundraising Campaign Calendar Plan
| Purpose | Medium | Responsible Party | Fundraising Activity/Theme | Fundraising Goal | Notes::
November/Pre-Launch
2021-11-01 | Thank | Email | Development/Stacey | Year in Review | - | Remind donors what we have been able to do despite COVID closure of our space
2021-11-04 | Thank | Phone | Board | Thank you call round, listen to donors |  | All week
2021-11-09 | Thank | Email/Social | Development/Stacey | Year in Review | - | What we did to help our community adapt to new realities.
2021-11-16 | Launch | Solicitation | Development/Stacey | State of the Organization | 2000 | To current donors only
2021-11-18 | Launch | Solicitation | Development/Stacey | State of the Organization | 1000 | To email list, non-donors
2021-11-25 | Launch | Thank | Development/Stacey | Why we're grateful for you |  | Post State of Org to Blog, share video update from ED to social media with link to blog
2021-11-30 | Thank | Thank | Development/Stacey | Prep for Giving Tuesday | -
Week 1
2021-12-01 | GIVING TUESDAY | Email & Social | Development/Stacey | We're still ready to grow | 5000 | Mention gift match
2021-12-02 | Engagement | Social | Marketing/Blaine | Participants/Student/Client/ Story | - | Sara's Story
2021-12-03 | Engagement | Social | Development/Stacey | Capital Campaign buildout update/photos | -
2017-12-04 | Engagement | Social | Marketing/Blaine | Impact stats | - | Engagement with our virtual programs
2021-12-05 | Engagement | Social | Marketing/Blaine | Participants/Student/Client/ Story | - | :Ryan's Story"
2021-12-06 | Engagement | Social | Volunteers | Social media ambassadors - share content | -
2021-12-07 | Ask | Email & Social | Development/Stacey | Supporting us will help the community grow back stronger; arts as economic driver | 1000
Week 2
2021-12-08 | Thank | Email & Social | Development/Stacey | We never stopped serving our community, and you never stopped supporting us | 1000 | Soft ask, but primarily thank you
2021-12-09 | Engagement | Social | Marketing/Blaine | Participants/Student/Client/ Story | -
2021-12-10 | Engagement | Social | Marketing/Blaine | Impact stats | -
2021-12-11 | Ask | Email & Social | Development/Stacey | Supporting us will help the community grow back stronger; arts as economic driver | 1500 | Mention gift match
2021-12-12 | Engagement | Social | Development/Stacey | Participants/Student/Client/ Story | -
2021-12-13 | Quiet Day |  |  | Re-asses campaign up to this point | -
2021-12-14 | Quiet Day |  |  | Re-asses campaign up to this point | -
Week 3
2021-12-15 | Engagement | Social | Development/Stacey | Update on raised vs. target | -
2021-12-16 | Ask | Email | Development/Stacey | Impact story | 3000 | Gift match central
2021-12-17 | Engagement | Social | Development/Stacey |  | -
2021-12-18 | Engagement | Social | Marketing/Blaine |  | -
2021-12-19 | Engagement | Social | Marketing/Blaine |  | -
2021-12-20 | Thank | Email & Social | Development/Stacey | We never stopped serving our community, and you never stopped supporting us | - | Soft ask, but primarily thank you
2021-12-21 | Engagement | Social | Marketing/Blaine |  | -
Week 4
2021-12-22 | Quiet Day | Social | Marketing/Blaine | Campaign Update | - | Give final numbers
2021-12-23 | Quiet Day | Social | Marketing/Blaine |  | -
2021-12-24 | Engagement | Social | Marketing/Blaine | Thank You | - | Mention gift match (if still happening)
2021-12-25 | Thank | Email | Marketing/Blaine | Thank You | - | Mention gift match (if still happening)
2021-12-26 | Engagement | Social | Marketing/Blaine | Thank You | - | Mention gift match (if still happening)
2021-12-27 | Ask | Email & Social | Development/ALL | Supporting us will help the community grow back stronger; arts as economic driver | 4000 | Mention gift match (if still happening)
2021-12-28 | Engagement | Social | Marketing/Blaine |  | -
Week 5
2021-12-29 | Engagement | Social | Marketing/Blaine | Campaign Update | - | Give final numbers
2021-12-30 | Ask | Email & Social | Development/Stacey | Campaign Update | 2000 | URGENT messaging
2021-12-31 | Ask | Email & Social | Development/Stacey | Campaign Update | 5000 | URGENT messaging
2022-01-01 | Thank | Email & Social | Marketing/Blaine | Thank you |  | Happy New Year!
Total

## Template
Year-End Fundraising Campaign Calendar Plan
| Purpose | Medium | Responsible Party | Fundraising Activity/Theme | Fundraising Goal | Notes
November/Pre-Launch
2021-11-01 | Thank |  | Development/Stacey | Year in Review | - | Remind donors what we have been able to do despite COVID closure of our space
2021-11-04 | Thank | Phone | Board | Thank you call round, listen to donors |  | All week
2021-11-09 | Thank | Email/Social | Development/Stacey | Year in Review | - | What we did to help our community adapt to new realities.
2021-11-16 | Launch | Solicitation | Development/Stacey | State of the Organization | 2000 | To current donors only
2021-11-18 | Launch | Solicitation | Development/Stacey | State of the Organization | 1000 | To email list, non-donors
2021-11-25 | Launch | Thank | Development/Stacey | Why we're grateful for you |  | Post State of Org to Blog, share video update from ED to social media with link to blog
2021-11-30 | Thank | Thank | Development/Stacey | Prep for Giving Tuesday | -
Week 1
2021-12-01 | GIVING TUESDAY | Email & Social | Development/Stacey | We're still ready to grow | 5000 | Mention gift match
2021-12-02 | Engagement | Social | Marketing/Blaine | Participants/Student/Client/ Story | - | Sara's Story
2021-12-03 | Engagement | Social | Development/Stacey | Capital Campaign buildout update/photos | -
2017-12-04 | Engagement | Social | Marketing/Blaine | Impact stats | - | Engagement with our virtual programs
2021-12-05 | Engagement | Social | Marketing/Blaine | Participants/Student/Client/ Story | - | :Ryan's Story"
2021-12-06 | Engagement | Social | Volunteers | Social media ambassadors - share content | -
2021-12-07 | Ask | Email & Social | Development/Stacey | Supporting us will help the community grow back stronger; arts as economic driver | 1000
Week 2
2021-12-08 | Thank | Email & Social | Development/Stacey | We never stopped serving our community, and you never stopped supporting us | 1000 | Soft ask, but primarily thank you
2021-12-09 | Engagement | Social | Marketing/Blaine | Participants/Student/Client/ Story | -
2021-12-10 | Engagement | Social | Marketing/Blaine | Impact stats | -
2021-12-11 | Ask | Email & Social | Development/Stacey | Supporting us will help the community grow back stronger; arts as economic driver | 1500 | Mention gift match
2021-12-12 | Engagement | Social | Development/Stacey | Participants/Student/Client/ Story | -
2021-12-13 | Quiet Day |  |  | Re-asses campaign up to this point | -
2021-12-14 | Quiet Day |  |  | Re-asses campaign up to this point | -
Week 3
2021-12-15 | Engagement | Social | Development/Stacey | Update on raised vs. target | -
2021-12-16 | Ask | Email | Development/Stacey | Impact story | 3000 | Gift match central
2021-12-17 | Engagement | Social | Development/Stacey |  | -
2021-12-18 | Engagement | Social | Marketing/Blaine |  | -
2021-12-19 | Engagement | Social | Marketing/Blaine |  | -
2021-12-20 | Thank | Email & Social | Development/Stacey | We never stopped serving our community, and you never stopped supporting us | - | Soft ask, but primarily thank you
2021-12-21 | Engagement | Social | Marketing/Blaine |  | -
Week 4
2021-12-22 | Quiet Day | Social | Marketing/Blaine | Campaign Update | - | Give final numbers
2021-12-23 | Quiet Day | Social | Marketing/Blaine |  | -
2021-12-24 | Engagement | Social | Marketing/Blaine | Thank You | - | Mention gift match (if still happening)
2021-12-25 | Thank | Email | Marketing/Blaine | Thank You | - | Mention gift match (if still happening)
2021-12-26 | Engagement | Social | Marketing/Blaine | Thank You | - | Mention gift match (if still happening)
2021-12-27 | Ask | Email & Social | Development/ALL | Supporting us will help the community grow back stronger; arts as economic driver | 4000 | Mention gift match (if still happening)
2021-12-28 | Engagement | Social | Marketing/Blaine |  | -
Week 5
2021-12-29 | Engagement | Social | Marketing/Blaine | Campaign Update | - | Give final numbers
2021-12-30 | Ask | Email & Social | Development/Stacey | Campaign Update | 2000 | URGENT messaging
2021-12-31 | Ask | Email & Social | Development/Stacey | Campaign Update | 5000 | URGENT messaging
2022-01-01 | Thank | Email & Social | Marketing/Blaine | Thank you |  | Happy New Year!
Total